## OUTLOOK OF KEY PROJECTS BY NNPC
S/N | Project Name | Contract Type | Lease/OML | Partner/Operator | Project Description | Project Scope | Project Status | Time line
1 | Bonga North | PSC | 118 | SNEPCO | BN Trache 1 project provide opportunity to unlock Bonga North development through tieback of 20 well pair to the extended BM FPSO by initially developing 327MMboe of recoverable Oil and keeping the FPSO full post 2027 to bring production of circa 120kbopd | EUR 327MMboe (in 9yrs) Capex $2.9Bln MOD 18km Subsea tieback to BM FPSO 14 New wells (7OP+7WI) New SURF 6 additional new wells as addendum to the initial FDP Total no of wells = 20 | FEED completed. Topside modification, PFRI and Subsea Hardware contracts EPC1, 2&3 are at tendering stage. | 2023 - 2027
2 | Bonga SouthWest-Aparo (BSWAP) | PSC | 118 | SNEPCO | Deep Water development in 1300m water depth. FPSO / Subsea system development with FPSO for 150kbopd. Phased development of 993MMbbls (590/210/193) and 23/20/20 wells for phases 1/2/3 respectively. | EUR 590/210/193 Mmboe Capex circa $9Bln Standalone FPSO 23/20/20 wells for phase 1/2/3 | Project still in framing stage. Thinking is to use leased FPSO as against Own. | 2027-2031
3 | Bonga New Oil Campaign | PSC | 118 | SNEPCo | New Oil Campaign to bring incremental production of circa 20kbopd through drilling of 2 oil producing wells and 3 Injectors | 1 producer well completed and hooked up, to come onstream immediately after Bonga 2022 TAM. 1 producer drilled to Intermediate section, look ahead is to drill to TD and complete. 3 Injectors drilled to Intermediate hole section, look ahead is to drill to TD and complete. | Drilling and hook up completed for one well. Batch drilling of 3 well onging. | Apr 22-Apr 23
4 | Bolia-Chota, Nnwa-Doro & Ngolo | PSC | 131/135 |  | Greenfield, major deep-water oil and gas development, located in Eastern offshore Nigeria, OMLs 135/131/129 in 700–1350m WD. Doro, Ngolo and Bolia fields, all non-producing. | Nnwa-Doro: 9 Tcf Gas + 175 MMbls Oil +145 MMbls condensate. Bolia-Chota: 241MMbls Oil +1.0 Tcf Gas 8 wells drilled in OML 135. Additional 2 wells each by OML 129 and OML 131 in the Nnwa-Doro and Boila-Chota units respectively. Pre-Unitisation Agreements signed Dec. 2013 (SNEPCO pre-unit Operator). Resource base of OML135 is material. PSC runs to 2023; | Endeavour still at conceptual stage. | TBD
5 | Owowo Development | PSC | 154 | ESSO | Greenfield, Major deep-water oil and gas development located 100km offhsore Niger Delta, in WD of about 700m. It straddles OML 139 and 154. Estimated 2P UR is 420.78 MMBO and 607.68 BSCF of Associated gas. | Drilling and completion of 53 producers/injectors (+13 contingent wells) with subsea tie-back to Usan FPSO. Usan FPSO Brown field modification | FIeld Development Planning Complete. FEED and Contracting to commence in 2024 | Owowo Phase 1: 2029 Owowo Phase 2: 2026 - 2032
6 | Bosi Development | PSC | 133 | ESSO | OML 133 is located approximately 110 km offshore west of Escravos, Nigeria and 160 km southeast of Lagos, Nigeria. In WD ranging from approximately 1400 m to 1600 m. Estimated 2P UR is 632 MMBO and 1,280 BSCF of Associated gas. | TBD | Field Development Planning in Progress | TBD
7 | Agbami Gas Monetization | PSC | 127/128 | Stardeep | Brownfield Project to increase the gas compression capacity on Agbami FPSO from 450 MMSCFD to 600 MMSCFD by adding an additional 150 MMSCFD compression module and to also build the upstream infrastructure to support the export of gas from the field. | Engineering, Procurement, Construction, Installation and Hook-up of Gas Turbine Compression (GTC)module, Gas Metering Unit GMU) and Instrument Air (IA) Skid, Subsea Equipment (Umbilical, UTA and ancillaries), Utilities upgrades (Nitrogen system, Cooling water cooler system and Cooling water recirculation pumps) and the provision of accomodation/installation vessel | Technical Phase of Tender | 2023-2027
8 | Preowei Development | PSC | 130 | TUPNI | Green field Project to Develop about 106MMBL (117MBOE) at expected peak production of about 55kbopd from Preowei field as a tie-back to Egina FPSO | - The project is to develop 2C resources of 106 MMbbls (117 MMboe) via sixteen (16) wells (8 Producers + 8 Water Injectors) as a circa 30 Km subsea tie-back to Egina FPSO. - The base case was for the flowline from Preowei to Egina to be a single pipeline subsea tie-in at the North Loop using Direct Electric Heating (DEH) technology or Electrically Traced Heated-Pipe-in-Pipe (ETH-PiP) technology for flow assurance | FEED earlier started 2019 but suspended Q1 2020 due to Covid-19 crises. FEED to restart Q1-2023. | Q1 2023 - Q3 2026
9 | ANOH Gas Development | JV | 21/53 | SPDC | Development of Asa-North and Ohaji-South Unit Area Gas resources | Drill 6 NAG wells & Install 300MMscf/d Gas processing plant for circa 250 MMscf/d gas production | Execution phase | Upstream Q3 2023 Midstream Q4, 2023
10 | Ubeta Gas Development | JV | 58 | TEPNG | Project is conceived to produce 10Msm3/d gas (8.3Msm3/d to NLNG and 1.7Msm3/d to domestic market) from Ubeta field and exporting it multiphase to Obite treatment center for processing and delivery to the target markets. | Installation of 10 slots unmanned wellhead platform with production capacity of 10MMscf/d from 6wells, Install Pig Luancher and Multi-phase flow meter. Contruct 16" x 11KM pipeline to Obite Treatment center | Basic Engineering | 2022- 2026
11 | Project Panther | JV | OMLs 49, 90, 91 & 95 | CNL | Project Panther scope consists mainly of 37-development infill wells, 4 well reactivations, pipelay for gas-lift & water injection, gas gathering and facilities hook-up across 8 offshore fields and 1 onshore field The program will monetize incremental 176 MMBOE (138 MMBO) resources/reserves, at a peak rate of 47 MBOEPD (36 MBOPD) by 2026 | 37 development wells across 8 JV Offshore fields & 1 Onshore field, comprising (32 Oil producers, 4 water injectors, 1 Gas well) & 4 well reactivations Delta South Gas Management (Flares-Out) Engineering, Design and Procurement and Installation of six (6) flexible flowlines. Engineering, procurement, fabrication, and installation to support facilities topsides jacket modifications which includes; Well sidetracks, Strap-on installation, Line repairs and line conversions (Oil to Gas & Gas to Oil) Site preps– includes dredging and hook-ups | Manufacturing of Flexible pipeline and modification of wellhead jacket ongoing | 2021 - 2026
12 | Agbami Rev 5 FDP Infill Drilling | PSC | 127/128 | STARDEEP | Plan to commence Agbami Rev 5 Field Development Plan Infill Wells project in 2025 to imrove Field recovery by ~75MMBO and commercialize 150MMSCF of Gas per day with the Expansion of Agbami Gas Handling Capacity to 600MMSCF per day | To Drill and complete a total of 12 wells (1o producers and 2 water injectors) | Field Development Planning in Progress | 2025-2027
13 | Madu Development | JV | 85 | First E&P | To develop the Madu field (OML 85) to achieve 16kbopd by Q4 2022. This will also allow for associated gas storage, circa 51MMSCF, for future utilisation thereby discntinuing flaring from the Anyala field. | Drilling and completion of Five (5) Oil production wells and a single gas injection well. Production shall be tied back to a floating production, storage and offloading facility (FPSO) | Madu CPS installed Drilling ongoing. Discussion ongoing for the SURF installation | 2020 - 2023